**Project Status Report**

|  |  |
| --- | --- |
| **Project Name** | Coded Messaging System |
| **Team Members** | Alan Cranbury, Mark Mahony |
| **Report Date** | October 12, 2012 |

**Project Overall Status: Green**

The FSK Mod – Demod is complete, as well as the UI design mockup in QT.

**Activities – During the Past Week**

|  |  |  |
| --- | --- | --- |
| **Activity** | **Planned Completion Date** | **% Complete** |
| Design FSK Mod Circuit | Wednesday, October 10, 2012 | 100% |
| Build FSK Mod Circuit | Thursday, October 11, 2012 | 100% |
| Debug FSK Mod Circuit | Friday, October 12, 2012 | 100% |
| Design FSK Demod Circuit | Wednesday, October 10, 2012 | 100% |
| Build FSK Demod Circuit | Thursday, October 11, 2012 | 100% |
| Debug FSK Demod Circuit | Friday, October 12, 2012 | 100% |
| UI Design | Friday, October 12, 2012 | 100% |

**Activities Planned – For the Next Week**

|  |  |
| --- | --- |
| **Activity** | **Planned Completion Date** |
| UI Implementation | Friday, November 2, 2012 |
| Design AFE | Wednesday, October 17, 2012 |
| Build AFE | Thursday, October 18, 2012 |
| Debug AFE | Friday, October 19, 2012 |
| Design Backbone Code | Wednesday, October 17, 2012 |
| Write Backbone Code | Thursday, October 18, 2012 |
| Debug Backbone Code | Friday, October 19, 2012 |

**Outstanding Issues**

|  |  |  |  |
| --- | --- | --- | --- |
| **Issue** | **Responsibility** | **Date to be Resolved** | **Proposed Resolution** |
|  |  |  |  |

**Changes to Plan**

|  |  |  |
| --- | --- | --- |
| **Change** | **Date of Change** | **Impact to Project** |
|  |  |  |
|  |  |  |